## Sheet1
ID | Category | Description | Probability (1-5) | Impact (1-5) | Risk Level | Owner | Response Strategy | Status
R1 | Technical | Garage sensors/hardware may report inaccurate occupancy data. | 3 | 3 | Medium | Infrastructure Team (Sensor Integration) | Mitigate - Provide option to manually override in case of discrepancies | Open
R2 | Technical | Third party mapping API may have downtime or limits. | 2 | 4 | Medium | Infrastructure Team (API Integration) | Mitigate -Provide fallback caching or directions if API goes down | Open
R3 | Technical | Payment gateway integration may fail or reject valid payment due to provider side changes. | 2 | 4 | Medium | Infrastructure Team (Payment Integration) | Mitigate - Include retry logic and monitor provider’s status page | Open
R4 | Technical | Synchronization in real time between the driver application and the operator dashboard could be slow or not work under heavy usage. | 2 | 3 | Medium | Infrastructure Team (Backend) | Mitigate - Perform load testing prior to Final Delivery milestone | Open
R5 | Technical | Interference from GPS/structure (concrete floor/underground floor) can result in inaccurate "last 50 feet" navigation. | 3 | 2 | Medium | Infrastructure Team (Mapping Integration) | Accept - An acceptable limitation; supplement by putting signs up at garage entrance | Open
R6 | Technical | The addition of multiple garages simultaneously can result in problems in database performance not seen during small scale testing. | 3 | 3 | Medium | Infrastructure Team (Backend/Database) | Mitigate - Conduct load testing early in process and scale horizontally | Open
R7 | Schedule | Long Infrastructure & Integrations phase might put off every dependent feature. | 3 | 4 | High | Project Manager | Mitigate - Closely monitor progress towards milestone; include scheduling buffer | Monitoring
R8 | Schedule | Third-party API onboarding (e.g., mapping or payments) might take more time than planned. | 2 | 3 | Medium | Infrastructure Team Lead | Mitigate - Start onboarding early; find backup providers | Open
R9 | Schedule | Driver App and Operator Dashboard teams might become misaligned if one of them delivers their part late. | 3 | 3 | Medium | Project Manager / Team Leads | Mitigate - Enforce contract of API between teams early | Open
R10 | Schedule | Testing & QA phase might be shortened because previous phases would overrun. | 3 | 3 | Medium | QA Team Lead | Mitigate - Protect QA phase timeline; escalate early in case other milestones fall behind | Open
R11 | Schedule | Bugs associated with Integration appear during Testing & QA but were not discovered when testing separately. | 4 | 3 | High | QA Team Lead | Accept - Already included in QA phase buffer | Open
R12 | Financial | Fees charged by the payment processor may be higher than anticipated. | 3 | 2 | Medium | Project Manager / Finance | Accept - Build fee into cost model | Open
R13 | Financial | Fees for mapping/navigation API may increase more than expected due to increased traffic. | 3 | 2 | Medium | Project Manager / Finance | Accept - Monitor usage; set up budget threshold alert | Open
R14 | Financial | The garage operators might not want to pay for premium dashboards features. | 3 | 3 | Medium | Product Owner | Mitigate - Validate price tiers by conducting pilot program with operators | Open
R15 | Financial | Cost overrun when extending the infrastructure phase if there are problems with integration. | 2 | 3 | Medium | Project Manager | Mitigate - Create budget contingency for Infrastructure Phase | Open
R16 | Financial | Unexpected legal fees when conducting legal reviews by the city parking compliance. | 2 | 3 | Medium | Project Manager | Transfer - Engage outside legal counsel as needed by city | Open
R17 | People | The main backend developer might decide to walk out of the project midway, delaying the infrastructure module because it is a blockage for all other modules. | 2 | 4 | Medium | Infrastructure Team Lead / PM | Mitigate - Thorough documentation of system; no single point of knowledge | Open
R18 | People | There could be misunderstandings among the Driver App and Operator Dashboard development teams, which could lead to duplicated work. | 3 | 2 | Medium | Project Manager / Team Leads | Mitigate - Enforce API contracts early between teams | Open
R19 | People | Slow response from the garage operator regarding garage occupancy information/data might delay testing. | 3 | 3 | Medium | Operator Dashboard Team | Mitigate - Set data submission deadline in Operator Onboarding Agreement | Open
R20 | People | Skill gap within the team with respect to the API of the selected payment service provider might delay implementation. | 2 | 3 | Medium | Infrastructure Team Lead | Mitigate - Include developer training period/documentation | Open
R21 | People | Communication silos amongst 4 different teams that will run in parallel, considering the scaling effect of communication channels with respect to team size. | 4 | 3 | High | Project Manager | Mitigate - Enforce regular meeting cadence | Open
R22 | People | Turnover of the garage operator company. | 2 | 2 | Low | Operator Dashboard Team | Accept - Low probability; re-onboard new contact in case of issue | Open