## Sheet1
|  |  |  | September | [29 empty] | October | [30 empty] | November
Task | Start | End | Duration | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24
Requirements and Kickoff | Sept. 1 | Sept. 10 | 10 Days
WBS & Scheduling | Sept. 11 | Sept. 17 | 6 Days
Infrastruce and Intergrations | Sept. 18 | Oct. 8 | 20 Days
Backend API and Database | Sep 22. | Oct. 1 | 10 Days
Mapping and Navigation | Oct. 2 | Oct. 12 | 10 Days
Payment Gate Intergration | Oct. 6 | Oct. 12 | 7 Days
Authentication | Sept. 25 | Oct. 5 | 1 Days
Garage Searches | Oct. 10 | Oct. 20 | 10 Days
Reservation | Oct. 10 | Oct. 22 | 12 Days
Payment | Oct. 10 | Oct. 22 | 12 Days
Notifications | Oct. 21 | Oct. 28 | 7 Days
User and Operator/ Garage Management | Sept. 25 | Oct. 15 | 20 Days
Reporting | Oct. 16 | Oct. 30 | 14 Days
Testing & QA | Nov. 1 | Nov. 17 | 16 Days
Final Delivery | Nov. 18 | Nov. 21 | 4 Days