- Software Requirements Specification (SRS)

- Project: GARK (Garage Parking Application)

- Version: 7.0

- Date: 10/07/2026

- Research

  - SpotHero

    - They are the main competitors across the country. They provide shown prices and a booked spot once you pay in advance. They seem to only target downtown areas. I can be better than them at allowing parking garages outside the limit to use as a “managing” tool instead.

  - ParkWhiz

    - Verry like SpotHero but with added focus to events and airport lots. One of their weaknesses is that they do not have a life update feed to actively show customers, which I can add to a better experience and faster efficiency.

  - ParkMobile

    - More focused on metered parking but offers garage management but with a bundle for everything. I think I can make it more garage focused, which will make it cheaper for those operators.

- Background

  - At first, employees were getting frustrated at a constantly overpacked parking garage. Regularly every morning employees would have to constantly circle the garage just to find a spot and not be late to work. Engineers in the office saw this struggle and began a prototype to track their garage parking spots in real time. This prototype was brought to a hackathon weekend where it showed a simple application tracking spot so employees can reserve a spot before leaving their house. It shocked the world and caught interest in building’s property management company because our employees stopped complaining about parking. They asked us to see if we could push this application to all their garages and it became the start of project GARK.

- 1. Introduction

  - 1.1 Purpose

    - GARK is to eliminate the time people waste on finding a parking spot within a garage. By allowing real-time updates on open spaces, reservation tools, and navigation. All from one source on your phone or website. Owners can monitor spaces, manage their pricing for a certain time frame, and create reports for them. We provide transparency for the customer and full management for the owners.

  - 1.2 Scope

    - Inside

      - Mobile and Web apps for open spaces

      - Real-Time updates

      - Advance reservation tool

      - Turn by Turn navigation.

      - Digital payment method

      - History with receipts

      - Operator admin board

    - Outside

      - MAYBE integration with garage hardware (gates, sensors, license plate reader)

      - Metered Parking

      - Legal enforcement

      - Repairs

      - Street traffic

      - Surface level parking lots

  - 1.3 The Company

    - We were founded by a small group of engineers that all came from UH. They spent years building internal tools for larger companies and noticed that the amazing work they did was going unnoticed and problem still not fully resolved. They left all their respected companies to come together to create something great. We are not focusing on a single tool to center point this company, No. We create problem solvers; we take on multiple small projects that can impact the world as we know it. We have built our reputation around for turning everyday frustrations into a simple mindless task.

- 2. Overall Description

  - Users: Drivers and garage operators

  - System Environment: Web-based and mobile applications

  - Constraints: Certain software connected to all garages, operator user authentication, data privacy, rely on other companies mapping.

  - Assumptions: Internet access, everyone has phones, companies willing to share data

- 3. Functional Requirements

  - FR1: The system shall allow people to register and login.

  - FR2: The system shall allow parking space reservation.

  - FR3: The system shall allow reservation history and receipts.

  - FR4: The system shall allow operators an administrative board.

  - FR5: The system shall allow digital payments.

  - FR6: The system shall allow real time space available.

  - FR7: The system shall allow operators to see occupancy and generate reports.

  - Etc.

- 4. Non-Functional Requirements

  - NFR1: The system shall update available spaces within 15 seconds of change.

  - NFR2: The system shall allow 750 concurrent users per network.

  - NFR3: The mobile app should support both IOS and Android.

  - NFR4: The system shall allow a new user to finish registering in 4 steps or less.

  - NFR5: The system should keep at payment transactions history.

  - NFR6: The system should have multiple languages for all people.

  - Etc.

- 5. Use Cases

  - 5.01 Title: Account Registering

  - Actor: User

  - Precondition: Does not have account set up

  - Steps:

    - 1. Opens web page or mobile app

    - 2. Clicks “Create an account.”

    - 3. Users enter their info and verify their email address

  - Postcondition: Customer has an active account and login permission

  - 5.02 Title: Login to account

  - Actor: User

  - Precondition: User has an active account

  - Steps:

    - 1. Users enter login information

    - 2. System verifies that information

    - 3. System grants access

  - Postcondition: User is logged in

  - 5.03 Title: Searching for open garage spaces.

  - Actor: User

  - Precondition: User is logged in

  - Steps:

    - 1. Enters and confirms destinations

    - 2. Systems pull together real time available spaces near that destination

    - 3. System shows a ranked list and a map of those garages with their prices.

  - Postcondition: User can see a list of availability

  - 5.04 Title: Viewing of garage locations.

  - Actor: User

  - Precondition: User performed the search

  - Steps:

    - 1. User chooses a garage

    - 2. System shows details of the garage

    - 3. Users see those details (pricing, hours, availability, height clearance)

  - Postcondition: User has all the information to make a choice

  - 5.05 Title: Reserving a parking space.

  - Actor: User

  - Precondition: User selected a garage

  - Steps:

    - 1. User sects estimate arrival and departure

    - 2. Users select number of hours (if garage does hourly pricing)

    - 3. System checks for availability

    - 4. User confirms space with reservation

    - 5. System temporary holds the space

  - Postcondition: User has created the reservation and pending payment

  - 5.06 Title: Paying for reservation.

  - Actor: User

  - Precondition: Pending payment

  - Steps:

    - 1. User selects payment method and enter their details

    - 2. System submit transaction to payment provider

    - 3. Payment provider confirms payment

    - 4. System confirms reservation and generates receipt for the user

  - Postcondition: Reservation is confirmed

  - 5.07 Title: Cancelling a reservation.

  - Actor: User

  - Precondition: User has a confirmed upcoming reservation

  - Steps:

    - 1. User opens active reservation

    - 2.  User clicks “Cancel Reservation.”

    - 3. System applies canceling policy

    - 4. System process refund to original payment method

  - Postcondition: Reservation is cancelled and space is open

  - 5.08 Title: Viewing reservation history.

  - Actor: User

  - Precondition: User has made past reservations

  - Steps:

    - 1. User clicks on “My Reservations.”

    - 2. System displays all past and current reservations

    - 3. User selects any reservations to view and get it receipts

  - Postcondition: User has access to history and receipts

  - 5.09 Title: Receiving reservations reminders.

  - Actor: User

  - Precondition: User has upcoming reservation

  - Steps:

    - 1. System monitoring their reservation time

    - 2. System send a push notification on a certain time before their reservation

    - 3. User received reminder

  - Postcondition: User gets reminded about their paid reservation

  - 5.10 Title: Viewing garage hours and their information.

  - Actor: User

  - Precondition: User selects a garage from their search

  - Steps:

    - 1. User clicks on the garage listing

    - 2. System shows the garages information (address, hours of operation, pricing, etc.)

  - Postcondition: User views information on chosen garage

  - 5.11 Title: Resetting forgotten password.

  - Actor: User

  - Precondition: User has an account but does not remember the password

  - Steps:

    - 1. Users click on “Forgot Password”

    - 2. Users enter the account’s email address

    - 3. Systems send a password reset link

    - 4. User creates new password

  - Postcondition: User can login with new password

  - 5.12 Title: operator adding a new garage listing.

  - Actor: Operator

  - Precondition: Operator has an approved operator account

  - Steps:

    - 1. Operator chooses “Add A Garage.”

    - 2. Operator enters garage name, address, hours, total space count, etc. (all information)

    - 3. Systems save the new garage and make it visible to users

  - Postcondition: New garages are available to users

  - 5.13 Title: Editing profile information.

  - Actor: User

  - Precondition: User is logged in

  - Steps:

    - 1. User selects “My Profile”

    - 2. User updates their name, email address, phone number, password, or payment methods

    - System saves that change and updates.

  - Postcondition: User profile will reflect any changes

  - 5.14 Title: Contacting the garage support.

  - Actor: User

  - Precondition: User has an issue with the garage or their reservation

  - Steps:

    - 1. User selects “Contact Support” on the garage reservation listing

    - 2. Users submit their issue

    - 3. System sends that message to the needed channels

  - Postcondition: User issues are logged and support responds

  - 5.15 Title: Logging out of account.

  - Actor: User

  - Precondition: User is logged in

  - Steps:

    - 1. User clicks on “Log Out”

    - 2. Systems end their session

  - Postcondition: User returned to login screen

WBS

- User Application (Frontend)

  - Estimated Duration: 31 Days (4.5 Weeks) (Sept. 29 – Oct. 29)

  - 1.1 – Authentication

    - Login

    - Registration

    - Session Managing

  - 1.2 – Garage Searching

    - Location searching

    - Listing of garages

    - Filter by price and availability

  - 1.3 – Reservations

    - Parking space reservation

    - Cancel or modify

    - History and receipts

  - 1.4 – Payments

    - Payment method

    - Checkout/ payment processing

    - Digital receipt (email/message)

  - 1.5 – Notifications

    - Reminders

Part, one covers the user interaction with the GARK application. Starting with creating an account then finding an open garage with spaces. Proceed to reserve a space then choosing payment of space (will be set by operator). They will then be notified about confirmation and given navigation to the garage. The user face team will do most of it and be done at the same time once the API backend is ready.

- Operator Dashboard (Backend)

  - Estimated duration: 36 Days (5 weeks) (Sept. 29 – Nov. 3)

  - 2.1 User – Operator Management

    - Add user account

    - Selects to add an operator account

    - Role based administration

  - 2.2 – Garage Management

    - Add, edit, and remove garages

    - Price management

    - Occupancy tracker

    - Photos and details (address, garage height, number of spaces + open, etc.)

  - 2.3 Reports

    - Occupancy (average, live tracker)

    - Revenue

    - Export financial records

Part two covers the tools the garage operator uses to run their garage business inside the GARK application. Operators can set the price and add a tracking system for spaces when user reserves. It also provides reports for operators for revenue and other data they want to see. This can be developed during the same time as the frontend.

- Infrastructure & Integrations

  - Estimated Duration: 21 Days (3 weeks) (Sept. 22 – Oct. 12)

  - 3.1 – Navigation

    - Turn directions by turn

    - Garage location pinning

  - 3.2 – Payment Gateway

    - Payment Provider Connection

    - Transaction security

  - 3.3 – Cloud Hosting

    - Backend API development

    - Database format

    - Server deployment

Part three covers the underlying systems that the user and operator can depend on to function. It has an application to connect third party mapping and payment providers. This is built after the two ends are finished.

Backlog

- Login

- Design login screen UI

- Implement email/password registration

- Implement security login authentication

- Create password resets

- Build session management (auto logout)

- Add “remember me” login option

- Add input validation/error message for login

- Email verification on signup

- Account lockout after continuing failing login attempts

- Social login (Google/Apple sign in)

- UI for Operator and Users

- User home screen layout

- Garage search (list view)

- Garage search (map view)

- Garage details page (basic information for users)

- Reservation confirmation message/screen

- Payment enters screen

- Digital receipt screen

- “My Reservation” history with receipts screen

- User profile/settings screen

- Notifications settings screen

- Operator dashboard

- “Add Garage” form UI for operators

- Garage price settings UI for operators

- Occupancy overview UI (operator side)

- Operator accounts settings

- Admin user management UI

- Onboarding/walkthrough for first time user

- Empty space screen

- Garage photo UI (operator side)

- Admin dashboard overview screen (different from operator dashboard)

- Backend Processes for Operator and User

- User authentication API endpoint

- Driver account creation and data storage

- Operator account creation and data storage

- API for searching and querying garages based on geolocation information

- Real-time availability logic

- API for making reservations

- Logic for canceling reservations and issuing refunds

- Integration with the payment processing service through API

- Logic for creating digital receipts

- Notifications (push/SMS)

- Garage CRUD API

- API for updating prices for operator users

- Role-based permission logic (admin/ operator/driver)

- Mapping and navigation API integration

- Database design for garages, users, and reservations

- Backend transactions logging

- Occupancy updates in real time using WebSocket or push technology.

- Retrying payments on transaction failure.

- Third-party API error handling and fallbacks in case of map or payment failures.

- Log for all administrative actions.

- Report for Operator and User

- Occupancy graph creation (backend process)

- Creation of revenue report (backend process)

- Reports on exports to PDF/CSV formats

- Reporting UI: date range selection

- Reporting UI: visual representation

- Reservation history report from a driver's perspective

- Platform usage report from an administrator's perspective

- Automated reporting: creation of weekly reports on schedule

- Caching/report optimization

- Restriction of reporting access to operators to their own garages only

- Filtering by multiple garages for operators in charge of several locations

- Report comparison: current and previous period

Jira Link:

https://gark.atlassian.net/jira/software/projects/KAN/boards/2?filter=type+IN+%28UI%2C+Reporting%2C+Login%2C+Backend%29&groupBy=none&atlOrigin=eyJpIjoiMmY1YWMyNGM0Y2MzNDQ3MmEzOGY4MjI1OGEwMWE4NDUiLCJwIjoiaiJ9

Technical Risks

- Garage sensors/hardware may report inaccurate occupancy data.

- Third party mapping API may have downtime or limits.

- Payment gateway integration may fail or reject valid payment due to provider side changes.

- Synchronization in real time between the driver application and the operator dashboard could be slow or not work under heavy usage.

- Interference from GPS/structure (concrete floor/underground floor) can result in inaccurate “last 50 feet” navigation.

- The addition of multiple garages simultaneously can result in problems in database performance not seen during small scale testing.

Schedule Risks

- Long Infrastructure & Integrations phase might put off every dependent feature.

- Third-party API onboarding (e.g., mapping or payments) might take more time than planned.

- Driver App and Operator Dashboard teams might become misaligned if one of them delivers their part late.

- Testing & QA phase might be shortened because previous phases would overrun.

- Bugs associated with Integration appear during Testing & QA but were not discovered when testing separately.

Financial Risks

- Fees charged by the payment processor may be higher than anticipated.

- Fees for mapping/navigation API may increase more than expected due to increased traffic.

- The garage operators might not want to pay for premium dashboards features.

- Cost overrun when extending the infrastructure phase if there are problems with integration.

- Unexpected legal fees when conducting legal reviews by the city parking compliance.

People Risks

- The main backend developer might decide to walk out of the project midway, delaying the infrastructure module because it is a blockage for all other modules.

- There could be misunderstandings among the Driver App and Operator Dashboard development teams, which could lead to duplicated work.

- Slow response from the garage operator regarding garage occupancy information/data might delay testing.

- Skill gap within the team with respect to the API of the selected payment service provider might delay implementation.

- Communication silos amongst 4 different teams that will run in parallel, considering the scaling effect of communication channels with respect to team size.

- Turnover of the garage operator company.

Meeting Cadence Per Team

Daily Stand-up — quick status check

Team Members: Driver App team, Operator Dashboard team, Infrastructure team, QA team

Structure: Three things from yesterday, three things from today, roadblocks

Bi/Weekly Progress Meeting — deep dive status check

Participants: One representative (team lead) from each of the four teams (Driver App, Operator Dashboard, Infrastructure, QA) + Project Manager

Purpose: As we are working in parallel based on the Gantt chart, here dependency roadblocks become apparent, like when the infrastructure team falls behind schedule, the Driver App and Operator Dashboard leads must be aware of this prior to becoming a problem

Monthly Sprint Meeting — stakeholders, high-level overview

Participants: Project Manager, team leaders from each team, external stakeholders (garage operator representatives, transportation department of city if relevant)

Purpose: High-level overview of Gantt milestones progress (Infrastructure ready, Driver App ready, Operator App ready, QA complete, final delivery)

Format: Demonstration of functionality, not just status report

Reporting Methods

| Target | What They Receive | Format |
| --- | --- | --- |
| Executives/Stakeholders | Progress against high-level milestones, status of budget/time, risks (high red items from Risk Register) | 1-page dashboard or summary slide |
| Garage Operators Stakeholders | Relevant feature pre-releases to them (dashboards, price tools), onboarding schedule | Live demo + short written update |
| Team Leads (User App, Operator, Infrastructure, QA) | Detailed tracking of tasks, issues, and dependencies | Jira board |
| Developers (within each team) | Task level tracking, bugs, technical specification | Jira board + daily stand-up notes |

Role & Resources

| Role | Name | Skill Level | Percentage Allocation | Work |
| --- | --- | --- | --- | --- |
| Project Manager | Charlotte Cheng | Senior | 50% | Oversee all 4 teams |
| Product Owner | Optimus Prime | Senior | 30% | Prioritization across teams |
| Business Analyst | Arcee | Mid | 25% | Requirements/SRS support |
| Architect | Megatron | Senior | 40% | System architecture, API design |
| Backend Developer 1 | Ironhide | Senior | 100% | Infrastructure |
| Backend Developer 2 | Soundwave | Mid | 100% | Infrastructure |
| Backend Developer 3 | Smokescreen | Mid | 80% | Operator Dashboard |
| Frontend Developer 1 | Sideswipe | Mid | 100% | Driver Application |
| Frontend Developer 2 | Hot Rod | Junior | 100% | Driver Application |
| Frontend Developer 3 | Starscream | Mid | 100% | Operator Dashboard |
| User Interface Designer | Jazz | Mid | 50% | Driver Application |
| Development Operation Engineer | Wheeljack | Mid | 60% | Infrastructure |
| QA Tester 1 | Peter Cullen | Mid | 100% | QA |
| QA Tester 2 | Bluestreak | Junior | 50% | QA |
| Subject Matter Expert (Parking Industry) | Alpha Trion | Senior | 10% | Consulted as needed |

Resource Plan

| Role | Name | Full-Time Equivalent Percentage | Estimated Hours | Hourly Rate | Cost |
| --- | --- | --- | --- | --- | --- |
| Project Manager | Charlotte Cheng | 50% | 240 | $90 | $21,600 |
| Product Owner | Optimus Prime | 30% | 144 | $90 | $12,960 |
| Business Analyst | Arcee | 25% | 120 | $65 | $7,800 |
| Architect | Megatron | 40% | 192 | $90 | $17,280 |
| Backend Developer 1 | Ironhide | 100% | 480 | $90 | $43,200 |
| Backend Developer 2 | Soundwave | 100% | 480 | $65 | $31,200 |
| DevOps Engineer | Wheeljack | 60% | 288 | $65 | $18,720 |
| Frontend Developer 1 | Sideswipe | 100% | 480 | $65 | $31,200 |
| Frontend Developer 2 | Hot Rod | 100% | 480 | $45 | $21,600 |
| UX Designer | Jazz | 50% | 240 | $65 | $15,600 |
| Frontend Developer 3 | Starscream | 100% | 480 | $65 | $31,200 |
| Backend Developer 3 | Smokescreen | 80% | 384 | $65 | $24,960 |
| QA Tester 1 | Peter Cullen | 100% | 480 | $65 | $31,200 |
| QA Tester 2 | Bluestreak | 50% | 240 | $45 | $10,800 |
| SME (Parking Industry) | Alpha Trion | 10% | 48 | $120 | $5,760 |
| TOTAL |  |  | 4776 |  | $325,080 |

| Item | Category | Quanty/Months | Unit Cost | Duration (months) | Total | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Team labor | Labor | 4,776 hours | varies by role | 3 | $325,080 | See Resource Plan tab |
| Cloud hosting | Infra | 1/month | $800 | 3 | $2,400 | Backend/API hosting |
| Licenses | Tools | one-off | $2,000 | N/A | $2,000 | IDE, Jira, design tools |
| Third-party APIs | APIs | one-off | $3,000 | N/A | $3,000 | Mapping + payment setup/usage |
| Hardware | Hardware | one-off | $1,500 | N/A | $1,500 | Test devices |
| Training | Training | one-off | $800 | N/A | $800 | Payment/mapping API onboarding |
| Overhead/Benefits | Overhead | 25% of labor | — | N/A | $81,270 | Per enterprise example formula |
| Subtotal |  |  |  |  | $416,050 |  |
| Contingency | Reserve | 15% of subtotal | — | N/A | $62,408 | Per lecture's 5-20% guidance |
| GRAND TOTAL |  |  |  |  | $478,458 |  |

Cost Plan

Monthly Cashflow

| Month | Labor | Infrastructure | Licenses/APIs/Hardware/Training | Overhead/Benefits | Contingency (15%) | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Month 1 (Sep) | $108,360 | $800 | $7,300 | $27,090 | $21,533 | $165,083 |
| Month 2 (Oct) | $108,360 | $800 | $0 | $27,090 | $20,438 | $156,688 |
| Month 3 (Nov) | $108,360 | $800 | $0 | $27,090 | $20,437 | $156,687 |
| TOTAL | $325,080 | $2,400 | $7,300 | $81,270 | $62,408 | $478,458 |